## QWebPageCheck
ID | LinkFromPage | CurrentPage (TestPage) | LinkToPage | Status | Description | Fix
1 | 127.0.0.1:800 |  | fpiweb/index | ok | login page
2 | login page | fpiweb/logout/ | fpiweb/index | problem | The LinkToPage should probably be the login page. If you follow the link to the main index page and click on fpiweb/manualmenu you get 'AnonymousUser object has no attribute profile' | JC – Current version just has link to login page. I didn’t have to change anything
3 | fpiweb/index | fpiweb/loc_row/ | fpiweb/index | ok as far as I got. | Stopped testing on this because I was not sure if I would muck up the DB | JC – I checked this page. I can add, edit and delete rows
4 | fpiweb/index | fpiweb/loc_bin/ | fpiweb/index | ok as far as I got. | Stopped testing on this because I was not sure if I would muck up the DB | JC – I checked this page. I can add, edit and delete bins
5 | fpiweb/index | fpiweb/constraints/ | fpiweb/index | ok as far as I got. | Stopped testing on this because I was not sure if I would muck up the DB | JC – Edit and Delete work OK. I got rid of row, bin, and tier constraints. Cannot add a constraint with the same name as existing constraint. Add and Delete options should probably me removed
6 | fpiweb/index | fpiweb/print_labels/ | none- has Generate PDF Button | Error | When Generate PDF button clicked with a number is 'Starting number' field you get following Error: TypeError at /fpiweb/print_labels/ __init__() missing 1 required positional argument: 'url_prefix' | JC – Currently getting the following error: 'QRCodePrinter' object has no attribute 'label_locations'. Fixing this bug would be part of 211
7 | fpiweb/index | fpiweb/test_scan/ | http://127.0.0.1:8000 | ok |  | JC – Got rid of TestScanView. It was a proof of concept from early in development
8 | fpiweb/index | fpiweb/test_scan/ | http://127.0.0.1:8000/fpiweb/box/box34568/ | ok | Goes to fpiweb/box/new/BOX34568/ page | JC – Got rid of TestScanView. It was a proof of concept from early in development
9 | fpiweb/index | piweb/test_scan/ | http://127.0.0.1:8000/fpiweb/box/box00012/ | Error | When LinkToPage clicked - message 'NoReverseMatch at /fpiweb/box/box00012/' | JC – Got rid of TestScanView. It was a proof of concept from early in development
10 | fpiweb/index | piweb/test_scan/ | fpiweb/index <index> | ok | Instead of 'index' most if not all links say 'Return to main page.' | JC – Got rid of TestScanView. It was a proof of concept from early in development
11 | fpiweb/index | piweb/test_scan/ | fpiweb/box/8/ <Box Details (empty box) | ok |  | JC – Got rid of TestScanView. It was a proof of concept from early in development
12 | fpiweb/index | piweb/test_scan/ | box/new/BOX34568/ <New Box> | ok |  | JC – Got rid of TestScanView. It was a proof of concept from early in development
13 | piweb/test_scan/ | box/new/BOX34568/ | Submit Button | Not sure | Not sure if this is supposed to be a mockup- 'Submit' button does not work correctly. 'Box number' field does not allow you to add input. | JC – I think this page is a reminant of early development. I think the plan was to have the QR code contain a link to a new box URL. This page will add a new box to the database. User gets directed to a user details page which wil display Box details, but move and empty buttons do not work.
14 | fpiweb/index | fpiweb/build_pallet/ | 'Select' not implemented | Not Implemented | Goes to page but page with fields but 'Select a Pallet' not implemented | JC – This has now been implemented
15 | fpiweb/index | fpiweb/build_pallet/ | 'Add' button | ???? | Unable to test this out due to QR scanning not working on local internet. See ID=41 to find results of this test | JC – Works when running on 127.0.0.1 IP address. Need to try this while integrated into Nginx
16 | fpiweb/index | fpiweb/build_pallet/ | fpiweb/index <Return to main page> | ok
17 | fpiweb/index | fpiweb/manualmenu/ | fpiweb/manualpalletmenu/ <Manage a pallet manually> | ok
18 | fpiweb/manualmenu/ | fpiweb/manualpalletmenu | <Select a pallet in progress> | not implemented |  | JC – Redirects to about page
19 | fpiweb/manualmenu/ | fpiweb/manualpalletmenu | <Start a New Pallet> | not implemented |  | JC – Redirects to about page
20 | fpiweb/manualmenu/ | fpiweb/manualpalletmenu | fpiweb/manualmenu/ Return to manual menu | ok
21 | fpiweb/manualmenu/ | fpiweb/manualboxmenu/ | fpiweb/manual_box_status/ <Check the status of a box> | ok
22 | fpiweb/manual_box_status/ | fpiweb/manual_box_status/ | Box number field with a value of '1' and 'Search' button clicked. | Error | AttributeError at /fpiweb/manual_box_status/ 'ExtantBoxNumberForm' object has no attribute 'get' | JC – Happens no box with the specified box number exists in the database. Form validation handles this. There’s some unnecessary error data in context (form has error information) and bootstrap-field in the template takes care of displaying the field error
23 | fpiweb/manual_box_status/ | fpiweb/manual_box_status/ | Box number field with a value of '12345' and 'Search' button | ok
24 | fpiweb/manual_box_status/ | fpiweb/manual_box_status/ | <Check another box> link clicked | ok
25 | fpiweb/manual_box_status/ | fpiweb/manual_box_status/ | /fpiweb/manualboxmenu/ <Return to Manual Box Menu> | ok
26 | /fpiweb/manualmenu/ | fpiweb/manual_add_box/ | Box number field with value of 12345 and Box type 'Banana' | ok
27 | /fpiweb/manualmenu/ | fpiweb/manual_add_box/ | Box number field with value of 12345 and Box type 'Banana' | ok UI funky | 2 error messages to user Box 12345 already in inventory
28 | fpiweb/manual_add_box/ | fpiweb/manual_add_box/ | fpiweb/manual_add_box/ <Add another box' link | ok
29 | fpiweb/manual_add_box/ | fpiweb/manual_add_box/ | piweb/manualboxmenu/ <Return to manual box menu> clicked | ok
30 | fpiweb/manual_add_box/ | fpiweb/manual_add_box/ | fpiweb/manualboxmenu/ <Cancel clicked> | ok
31 | fpiweb/manual_add_box/ | fpiweb/manual_add_box/ | fpiweb/manual_add_box/ Box number field with a value of '123456' | Error | InvalidValueError at /fpiweb/manual_add_box/ 101 - Box number of "BOX123456" is improperly formatted or missing
32 | /fpiweb/manualboxmenu/ <Check In Box> | fpiweb/manual_checkout_box/ <Check In Box> | fpiweb/manual_checkout_box/ | Probable link error | Checkin Box link goes to fpiweb/manual_checkout_box/ is this correct? Also 2 error messages to user.
33 | /fpiweb/manualboxmenu/ <Checkout Box> | fpiweb/manual_checkout_box/ | fpiweb/manual_checkout_box/ with 'Box number' field tested with '12345' | ok | 2 error messages to user should probably only have one
34 | /fpiweb/manualboxmenu/ <Checkout Box> | /fpiweb/manualboxmenu/ <Checkout Box> | with 'Box number' field tested with '123456' | Not Defined | 2 error messages to user stating 'box is empty or missing' Probably should state 'box number invalid'
35 | /fpiweb/manualboxmenu/ <Checkout Box> | /fpiweb/manualboxmenu/ <Cancel Box Consumption> | fpiweb/manual_checkout_box/ | pk
36 | fpiweb/manualboxmenu/ <Move a box> | fpiweb/manual_move_box/ | fpiweb/manual_move_box/ 'Box number' field tested with '12345' | Error | One user error message states 'Box number invalid' while the other user error message states ' .. Is empty'. Correct message should be '…is empty'.
37 | fpiweb/manualboxmenu/ <Move a box> | fpiweb/manual_move_box/ | fpiweb/manual_move_box/ 'Box number' field tested with '123456' | Error | One user error message states 'Box number invalid' while the other user error message states ' .. Is not present in the database'. Correct message should be 'Box number invalid'.
38 | fpiweb/manual_move_box/ | fpiweb/manual_move_box/ <Cancel Box Move> | fpiweb/manualboxmenu/ | ok
39 | fpiweb/manualboxmenu/ | fpiweb/manualboxmenu/ <Return to manual menu> | fpiweb/manualmenu/ | ok
40 |  | fpiweb/manualmenu/ | fpiweb/index/ | ok
41 | fpiweb/index | fpiweb/build_pallet/ | 'Select Button' | UI issue | Select has no choices until you enter something into the 'Name of pallet' text field below- might want to give the user a hint that select can't be used until the 'Name of pallet' text field in the DB is populated with data. Need to rethink UI here.
42 | fpiweb/index | fpiweb/build_pallet/ 'Name of Pallet' + 'Add Button' clicked | fpiweb/build_pallet | UI issue | This is confusing for me- I can add anything in text in the 'Name of Pallet' field/ Might help to give the user a clue
43 | fpiweb/build_pallet/ 'Name of Pallet' + 'Add Button' clicked | fpiweb/build_pallet/ 'Scan' button clicked | QR screen popup | ok
44 | fpiweb/build_pallet/ 'Scan' button clicked | QR screen popup- User presents Qrcode and clicks on Scan | QR screen popup presents 'Scan Failed' popup | Error | Not sure about this- in previous testing on my machine I have encountered frequent failures- May be due to incorrect setup on my laptop
45 | QR screen popup presents 'Scan Failed' popup | Scan failed' popup- click on 'OK' button | Popup disappears | ok
46 | fpiweb/build_pallet/ 'Scan' button clicked | QR screen popup- click on 'Close' Button | fpiweb/build_pallet | ok
47 | fpiweb/build_pallet/ 'Scan' button clicked | QR screen popup- 'key in box number' + 'Scan' button clicke | Error pop up | Error | message 'DoesNotExist at /fpiweb/box/box_form/ Constraints matching query does not exist'